## Read
Porject Title: |  | Video Analytics at the Edge
No | Student Name ( First, Last ) | email | Faculty (First, Last) | email
1 | Luke, Barber | lukebarber@usf.edu | Yasin, Yilmaz | yasiny@usf.edu
2 | Mikel, Castano | holmquist@usf.edu
3 | Shawn, Sheng | shawnsheng@usf.edu
4
Please DO NOT change the format of this template
For any update or changes instructor will provide update to the template, as deemed necessary.
File Name should be : Project Name Titles_Last Names or initials of team members
This report is cumaltive, and you should add/update this and submit to canvas. Add extension to it to align with the report number due.
Please work with your team member(s) to update this and weekly basis, the purpose of this sheet is to keep all team members aligned and up to date.

## Action Register
Minimum one action item per team member per week | [7 empty] | Provide short status in a bulletize forms Closure plans? Why delay?
# | Date Created | Originator | Description | Assignee | Original Due Date | Status | Updated Due Date | Status and Closure Comments | Aging
1 | 2022-09-08 | Shawn | Arrange Meeting with faculty advisor | ALL | 2018-01-23 | Closed | 2018-01-23 | Meet Advisor 2:30 ENB his office
2 | 2022-09-08 | Luke | Meet Faculty advisor | ALL | 2022-09-08 | Closed | 2022-09-08 | Introduction to machine learning and new tasks on familarizing the subject before going forward.
3 | 2022-09-08 | Dr. Yilmaz | Familiarize with PyTorch, Neuronetworks, and classical machine learning approaches | ALL | 2022-09-15 | Open |  | Currently all member working on becoming more familar with NN
4 | 2022-09-15 | Mikel | Establish weekly teleconference/meeting | ALL | 2022-09-15 | Closed | 2022-09-15 | Team aggreed to meet on weekends online and meet with faculty advisor on thursdays.
5 | 2022-09-22 | Dr. Yilmaz | Continue learning programming and theory behind AI | ALL | 2022-09-29 | Closed | 2022-09-29 | Currently all member working on becoming more familar with NN
6 | 2022-09-29 | Dr. Yilmaz | Continue learning programming and theory behind AI | ALL | 2022-10-06 | Closed | 2022-10-06 | Currently all member working on becoming more familar with NN
7 | 2022-10-06 | Dr. Yilmaz | Continue learning programming and theory behind AI | ALL | 2022-11-04 | Closed | 2022-11-04
8 | 2022-10-06 | Shawn | Establish Bill of material | Shawn | 2022-11-04 | Closed | 2022-11-13 | Initial list of materials
9 | 2022-10-06 | Luke | Meet to create a definite plan for project | ALL | 2022-11-04 | Closed | 2022-11-27
10 | 2022-10-06 | Mikel | Become familiar with some libraries utilized in Machine Learning Algorithms | Mikel | 2022-11-04 | Closed | 2022-11-11 | There are several options that we could use, but we will focus on using Pytorch
11 | 2022-10-17 | Luke | Complete parts 4,7,9,10 of SRD | Luke | 2022-10-24 | Closed | 2022-10-24
12 | 2022-10-17 | Luke | Complete parts 6, 8 of SRD | Shawn | 2022-10-24 | Closed | 2022-10-24
13 | 2022-10-17 | Luke | Complete parts 2,3 of SRD | Mikel | 2022-10-24 | Closed | 2022-10-24
14 | 2022-10-17 | Luke/Shawn | Get Jetson Nano up and running | Shawn | 2022-10-21 | Closed | 2022-10-17 | Jetson Nano OS loaded
15 | 2022-10-17 | Mikel | Explore possibility of utilizing Raspberry Pi | Mikel | 2022-10-17 | Closed | 2022-11-11 | Raspberry Pi should be responsible for doing server work and will communicate with the jetson directly
16 | 2022-10-24 | Luke | Load a basic program onto the Jetson Nano | Luke | 2022-11-04 | Closed | 2022-11-11 | Loaded basic OpenCV program
17 | 2022-11-06 | Mikel | Explore different cameras and architectures | Mikel | 2022-11-12 | Closed | 2022-11-19 | Any USB camera could be used for training the algorithm, but a MIPI camera would be ideal for this project
18 | 2022-11-06 | Luke/Shawn | Create programs and test on Jetson Nano | Shawn | 2022-11-21 | Open | 2022-12-08 | Pipeline from USB Camera to OpenCV running on linux complete, next step is throwing it into ML
19 | 2022-11-10 | Shawn | Check and service aerial platform | Shawn | 2022-11-18 | Closed | 2022-12-08 | Serviced autopilot, checked motor function
20 | 2022-11-10 | Shawn | Design Camera Enclosure in Fusion/Inventor | Shawn | 2022-11-18 | Closed | 2022-12-08
21 | 2022-11-10 | Shawn | Drawing and render for camera Enclosure and | Shawn | 2022-11-18 | Open | 2022-12-08
22 | 2022-11-10 | ALL | Work on PDR and finialize SDR | ALL | 2022-11-20 | Open
23 | 2022-11-16 | Luke | Perform image filtering with color masking | Luke | 2022-11-20 | Closed | 2022-12-08
24 | 2022-11-20 | Luke | Compare Pi Cam and Webcam | Mikel | 2022-11-23 | Open
25 | 2022-11-20 | Mikel | Update Bill of Materials | Mikel | 2022-11-20 | Closed | 2022-12-21 | Added more materials and links to websites
26 | 2022-11-20 | Mikel | Start training AI model | Mikel | 2022-12-07 | Open |  | Train first AI model to get used to programming language (Python) and libraries (Pytorch)
27 | 2022-11-20 | Shawn | Create physical model in CAD | Shawn | 2022-12-05 | Closed | 2022-12-05
28 | 2022-11-28 | Luke | Trace objects with image overlays | Luke | 2022-12-08 | Open | 2022-12-08
29 | 2022-11-28 | Mikel | Preliminary AI Tests | Mikel | 2022-12-08 | Open | 2022-12-08
30 | 2022-11-28 | Shawn | 3D Print physical model prototype | Shawn | 2022-12-08 | Open | 2022-12-08
31 | 2022-11-21 | ALL | Finish SRD and PDR | ALL | 2022-12-05 | Closed | 2022-12-05

## Accomplishments
Tri-Weekly status. The content of the weekly communication is: a) Program schedule, technical and cost status b) Significant accomplishments c) Issues and resolution plans d) Action items status e) Provide date and time of meeting with the advisor The purpose of this document is for the individual function Team/leads to provide current status in their specific area to be included in the project status Need to provide progress against, at minimum: SRD, SRR, PDR, Website, schedule, WBS, BOM etc.
This Column tracks your significant accomplishments. You can use this to sub-tasks from your scheduled progress.
# | Week of Accomplishments | Description of Accomplishment | Notes
1 | 2022-09-08 | Meet with Dr. Yilmaz and team to coordinate new product development | Two types of anomolies: object type, speed type
1 |  |  | begin researching optical flow and object recognition
1 |  |  | Potential softwares: Yolo.v4, OpenCV (object recognition); PyTorch, Keras, TensorFlow
2 | 2022-09-15 | Self teach and team learning of machine learning. | Continuation of prior week
3 | 2022-09-22 | Self teach and team learning of machine learning. | Spoke to academic advisor via email and advisor gave super good input on the materials on what we are looking at and the materials
4 | 2022-09-29 | Activities cancelled due to Hurricane Ian
5 | 2022-10-06 | Self teach and team learning of machine learning. | Assembled the machine learning hardware.
6 | 2022-10-13 | Self teach and team learning of machine learning. | Ran machine learning on the hardware, training our first models.
7 | 2022-10-17 | loaded OS onto Raspberry Pi
8 | 2022-10-17 | Jetson Nano operational
9 | 2022-10-24 | SRD Document Verison 1.1 completed
10 | 2022-10-24 | Understanding of Multi-layered learning, Deep Learning, weights and biases, sigmod and ReLex operators. | These learning objects are a deep dive in how neuronetwork works. We are focusing on theory, rather than just running an algorithm on a computer and not knowing how it works.
11 | 2022-10-31 | Understanding of Gradient decent and training a nuero-networking using backpropagation. | These are critical objectives in designing, training, and fine-tuning our own or an exsist machine learning model.
12 | 2022-11-07 | Open CV running at linux enviroment | OpenCV running at a linux enviroment is the hallmark of everything we do in software. From this, traditional methods in video analytics in edge computing is done. We've de-facto performed "edge computing". Using more advanced algorithms, such as a ML network, follows.
13 | 2022-11-14 | Aerial/Physical Platform Operational | Examined possibility of utilizing aerial platform
14 | 2022-11-17 | Performed preliminary tests with the Jetson Nano and Image filtering | Color scaling
15 | 2022-12-21 | Created a CAD model for physical system | 3D CAD Model for the physical system that will house the hardware used in the project
16 | 2022-12-21 | PDR Presentation | PDR Presentation for class
17 | 2022-12-04 | Completed SRD Document | Complete, ensure the document is up-to-date, and review the SRD Document

## Project Schedule
This is notional template and dates need to alighn with class desginated dates and deadlines. As a team you need to further break down class deadlines to keep your team on track
| Desing I | [16 empty] | Design II - subject to change per design II Intructor
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Needs to Align with Instructors deadlines
Intructors Milestones
[11 empty] | SRD due |  |  |  |  | PDR |  |  |  | CDR | [11 empty] | Design Demonstration
Team Formation and Advisor established
WBS, Org. and Schedule due, embeded in excel
Requirements Doc Due ( Preliminary & Final )
Final Document Package due
Team/Student needs to provide further schedule detial to accomplish the tasks
Planning and Systems Engineering
Product Idea/Concept
System Engineering Managent Plan
System Requirements Document (SRD)
Design Document
Major Design Deadlines | Design II - subject to change per design II Intructor 22: Procure
Design, Procure, Build, & Test | Design II - subject to change per design II Intructor 25: Build; Design II - subject to change per design II Intructor 31: Test
Sub Design and Development Tasks
Sub task 01
Sub task 02
Sub task 03
Sub task 04
Assumptions:
Understanding of Machine Learning

## WBS
Team | Need to break down task so a single individual is responsible. For example, EE task can be broken for two individuals or more, as needed | By writing this, team member agrees to the task assignment | By writing this, team member agrees to the task assignment
Roles | Responsible Individual | TASK DESCRIPTION - Design I | TASK DESCRIPTION - Design II
MANAGEMENT |  |  |  | write the perceived detail
Technical Leader | Luke | Keep up to date with technical information and the application thereof to the project
Team Coordination Leader | Shawn | Coordinates Assets, Plans, and Time
Cost & Schedule leader | Mikel | Updates the schedules on this sheet and manages fiances during making purchasing decisions
SYSTEM ENGINEERING
SYST ENGINEERING | Luke | This is a collaborative effort because our team is small and the task at hand is quite broad (applying machine learning). Each student will be tasked to learn as much as he can and help each other to be familar with the concepts of machine learning. |  | Example: SEMP Document
SYST ENGINEERING | Mikel | This is a collaborative effort because our team is small and the task at hand is quite broad (applying machine learning). Each student will be tasked to learn as much as he can and help each other to be familar with the concepts of machine learning. |  | Example: Requirements Documents
TEST ENGINEERING | Shawn | Shawn will be responsible in testing the system to see if it meets the expected requirements.
PROD ENGINEERING | Mikel
CONFIG MGMT | Luke
RELIABILITY | Shawn | Shawn will be responsible in testing the system agasint expected enviroments. If the team decides to shift to building a robot, then Shawn will take the vehicle to subject it to noises expected.
QUALITY | Mikel
PARTS MANAGEMENT | Luke
EMI / EMC | Shawn | Shawn will take account of EMI and EMC . If there are no equipments avalible to test these systems due to finanical restrictions, then theoritcal considerations and best practices will be implemented.
SAFETY | Mikel
Hardware
ELECT.DESIGN |  | All members will help distribute the task since it is such a small team.
DESIGN | Luke | Luke will focus on electrical hardware design.
MECH. DESIGN
PSNA DESIGN | Shawn | Shawn will focus on mechanical design.
SOFTWARE
SW DEVELOPM | Mikel | Mikel will focus on the software design of the system.
TEST Engineering
Test | Shawn | As mentioned above, shawn will perform and design tests for the system.
TEST SOFTWARE
DESIGN | Mikel | Mikel will perform and design tests for the software of the system.

## BOM
Index | Component Name | Short description | function, how it is used in your system | Quantity | Cost | Reference or links to websites
1 | Jetson Nano Dev Kit | NVIDIA Jetson Nano Developer Kit-B01 | Jetson Nano. Used for hight speed video processing | 1 | 149 | https://www.seeedstudio.com/NVIDIA-Jetson-Nano-Development-Kit-B01-p-4437.html
2 | Raspberry Pi | Pi 4 4GB Starter Kit | Raspberry Pi. Will be used to access the programmed algorithms | 1 | 119.95 | https://www.canakit.com/raspberry-pi-4-4gb.html?cid=usd&src=raspberrypi
3 | PI cam | Raspberry Pi Camera Module V2 | Used to take video feed | 1 | 29.95 | https://www.pishop.us/product/raspberry-pi-camera-module-v2/?src=raspberrypi
4 | HDMI Monitor | Full HD (1920 x 1080) HDMI monitor | Used to help the coding of the RasPi and Nano. Additionally will be used to display camera feed | 1 | 99.99 | https://www.amazon.com/Acer-SB220Q-Ultra-Thin-Frame-Monitor/dp/B07CVL2D2S/ref=asc_df_B07CVL2D2S/?tag=&linkCode=df0&hvadid=309751315916&hvpos=&hvnetw=g&hvrand=2984751961022005895&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9012103&hvtargid=pla-623140191247&ref=&adgrpid=67183599252&th=1
5 | HDMI Cable | HDMI Cable (6 ft) | Connect between the Jetson/RasPi and the monitor. | 1 | 6.5 | https://www.amazon.com/dp/B074FFM8NH/ref=asc_df_B074FFM8NH1668942000000?tag=cnet-buy-button-20&creative=395261&creativeASIN=B074FFM8NH&linkCode=asn&ascsubtag=4488de497d3f43d9b028b7b709b91106%7C0c51f952-23c5-46b9-9981-e666ddffc904%7Cdtp&th=1
6 | USB Cable | USB 3.0 Male to Male Type A (1.5 ft) |  | 1 | 6.99 | https://www.amazon.com/UGREEN-Transfer-Enclosures-Printers-Cameras/dp/B00P0E3954/ref=sr_1_2_sspa?gclid=Cj0KCQiAveebBhD_ARIsAFaAvrGmKD_6BYiGSyBMaOykmtG-7y-5g0AYURXQmgAFIiLV0Cve6tTJt_YaAvKmEALw_wcB&hvadid=616863166062&hvdev=c&hvlocphy=9012103&hvnetw=g&hvqmt=e&hvrand=7260197836364059012&hvtargid=kwd-2739326421&hydadcr=24662_13611802&keywords=usb%2Busb%2Bcable&qid=1668991145&sr=8-2-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&th=1
7 | USB Keyboard | Basic USB Keyboard | Used to help the coding of the RasPi and Nano. | 1 | 10.77 | https://www.amazon.com/AmazonBasics-Matte-Keyboard-QWERTY-Layout/dp/B07WJ5D3H4/ref=asc_df_B07WJ5D3H4/?tag=&linkCode=df0&hvadid=416694317409&hvpos=&hvnetw=g&hvrand=15199027512185915176&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9012103&hvtargid=pla-913716436783&ref=&adgrpid=94693386435&th=1
8 | USB Mouse | Basic USB Mouse | Used to help the coding of the RasPi and Nano. | 1 | 5.99 | https://www.amazon.com/Verbatim-Optical-Mouse-Accessibility-Compatible/dp/B00LPC3O3M/ref=sr_1_2_sspa?gclid=Cj0KCQiAveebBhD_ARIsAFaAvrHfeKxsZjww1gb-U-z-6kcb3bJSpWOKb5n6JWqrnU4v5QbZ4l-awHcaAuE6EALw_wcB&hvadid=616863247161&hvdev=c&hvlocphy=9012103&hvnetw=g&hvqmt=e&hvrand=16760430086096392764&hvtargid=kwd-2510389481&hydadcr=26614_11715055&keywords=usb+mouse&qid=1668992084&sr=8-2-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&psc=1
9 | 5V/3A Power Supply | Raspberry Pi 4 Model B Official PSU | Power supply for Raspberry Pi | 1 | 7.99 | https://www.amazon.com/Raspberry-Model-Official-SC0218-Accessory/dp/B07W8XHMJZ
10 | 5V/4A Power Supply | Power Supply for Jetson Nano | Power supply for Jetson Nano | 1 | 12.99 | https://www.amazon.com/waveshare-Supply-100-240V-Adapter-Converter/dp/B0915J7BXL/ref=sr_1_7?crid=2PH8HGAJ73D1P&keywords=12v+power+supply+jetson+nano&qid=1668993724&sprefix=12v+power+supply+jetson+nano%2Caps%2C419&sr=8-7
11 | 128gb MicroSD | SanDisk 128GB Ultra microSD | Memory Cards for Jetson Nano and Raspberry Pi | 2 | 35.3 | https://www.amazon.com/SanDisk-128GB-MicroSDXC-Memory-Adapter/dp/B0B7NTY2S6/ref=sr_1_5?gclid=Cj0KCQiAveebBhD_ARIsAFaAvrE08_fvhgToguZZ98vGk_q1sMuLYPPigwQ2reVOTupXX_kbTzz0IhcaAvLqEALw_wcB&hvadid=557586749177&hvdev=c&hvlocphy=9012103&hvnetw=g&hvqmt=e&hvrand=15603730328294678755&hvtargid=kwd-31052172773&hydadcr=18003_13447347&keywords=128gb%2Bmicrosd&qid=1668991406&sr=8-5&th=1
12 | Jetson Nano Wireless Internet Adapter | Jetson Nano WiFi Adapter Dual Band Wireless USB 3.0 | Gives the Jetson Nano Wireless Internet Access | 1 | 18.99 | https://www.amazon.com/Geekworm-Adapter-Wireless-1200Mbps-Network/dp/B07TFT876R
13 | Jumper Wires | Jumper Wires | Used to power peripherals. Especially cooling fans | 120 | 6.98 | https://www.amazon.com/Elegoo-EL-CP-004-Multicolored-Breadboard-arduino/dp/B01EV70C78/ref=asc_df_B01EV70C78/?tag=hyprod-20&linkCode=df0&hvadid=222785939698&hvpos=&hvnetw=g&hvrand=13549122753249701448&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9012103&hvtargid=pla-362913641420&psc=1
14 | Ethernet Cable | Ethernet Cable Cat 7 (6.5 ft) | For communication between Raspberry Pi and Jetson | 2 | 8.99 | https://www.amazon.com/Ethernet-VANDESAIL-Gigabit-Network-Plated/dp/B01H4U8XZ2?tag=edit-tech-round-up-20&th=1&ascsubtag=00lMU4uHB7M4e8DPIkkcgRW