## Read
Project Title: |  | Video Analytics at the Edge
No | Student Name ( First, Last ) | email | Faculty (First, Last) | email
1 | Luke, Barber | lukebarber@usf.edu | Yasin, Yilmaz | yasiny@usf.edu
2 | Mikel, Castano | holmquist@usf.edu
3 | Shawn, Sheng | shawnsheng@usf.edu
4
Please DO NOT change the format of this template
For any update or changes instructor will provide update to the template, as deemed necessary.
File Name should be : Project Name Titles_Last Names or initials of team members
This report is cumaltive, and you should add/update this and submit to canvas. Add extension to it to align with the report number due.
Please work with your team member(s) to update this and weekly basis, the purpose of this sheet is to keep all team members aligned and up to date.

## Action Register
Minimum one action item per team member per week | [7 empty] | Provide short status in a bulletize forms
Closure plans?
Why delay?
# | Date Created | Originator | Description | Assignee | Original Due Date | Status | Updated Due Date | Status and Closure Comments | Aging
1 | 2022-09-08 | Shawn | Arrange Meeting with faculty advisor | ALL | 2018-01-23 | Closed | 2018-01-23 | Meet Advisor 2:30 ENB his office
2 | 2022-09-08 | Luke | Meet Faculty advisor | ALL | 2022-09-08 | Closed | 2022-09-08 | Introduction to machine learning and new tasks on familarizing the subject before going forward.
3 | 2022-09-08 | Dr. Yilmaz | Familiarize with PyTorch, Neuronetworks, and classical machine learning approaches | ALL | 2022-09-15 | Open |  | Currently all member working on becoming more familar with NN
4 | 2022-09-15 | Mikel | Establish weekly teleconference/meeting | ALL | 2022-09-15 | Closed | 2022-09-15 | Team aggreed to meet on weekends online and meet with faculty advisor on thursdays.
5 | 2022-09-22 | Dr. Yilmaz | Continue learning programming and theory behind AI | ALL | 2022-09-29 | Closed | 2022-09-29 | Currently all member working on becoming more familar with NN
6 | 2022-09-29 | Dr. Yilmaz | Continue learning programming and theory behind AI | ALL | 2022-10-06 | Closed | 2022-10-06 | Currently all member working on becoming more familar with NN
7 | 2022-10-06 | Dr. Yilmaz | Continue learning programming and theory behind AI | ALL | 2022-11-04 | Closed | 2022-11-04
8 | 2022-10-06 | Shawn | Establish Bill of material | Shawn | 2022-11-04 | Closed | 2022-11-13 | Initial list of materials
9 | 2022-10-06 | Luke | Meet to create a definite plan for project | ALL | 2022-11-04 | Closed | 2022-11-27
10 | 2022-10-06 | Mikel | Become familiar with some libraries utilized in Machine Learning Algorithms | Mikel | 2022-11-04 | Closed | 2022-11-11 | There are several options that we could use, but we will focus on using Pytorch
11 | 2022-10-17 | Luke | Complete parts 4,7,9,10 of SRD | Luke | 2022-10-24 | Closed | 2022-10-24
12 | 2022-10-17 | Luke | Complete parts 6, 8 of SRD | Shawn | 2022-10-24 | Closed | 2022-10-24
13 | 2022-10-17 | Luke | Complete parts 2,3 of SRD | Mikel | 2022-10-24 | Closed | 2022-10-24
14 | 2022-10-17 | Luke/Shawn | Get Jetson Nano up and running | Shawn | 2022-10-21 | Closed | 2022-10-17 | Jetson Nano OS loaded
15 | 2022-10-17 | Mikel | Explore possibility of utilizing Raspberry Pi | Mikel | 2022-10-17 | Closed | 2022-11-11 | Raspberry Pi should be responsible for doing server work and will communicate with the jetson directly
16 | 2022-10-24 | Luke | Load a basic program onto the Jetson Nano | Luke | 2022-11-04 | Closed | 2022-11-11 | Loaded basic OpenCV program
17 | 2022-11-06 | Mikel | Explore different cameras and architectures | Mikel | 2022-11-12 | Closed | 2022-11-19 | Any USB camera could be used for training the algorithm, but a MIPI camera would be ideal for this project
18 | 2022-11-06 | Luke/Shawn | Create programs and test on Jetson Nano | Shawn | 2022-11-21 | Closed | 2022-12-08 | Pipeline from USB Camera to OpenCV running on linux complete, next step is throwing it into ML
19 | 2022-11-10 | Shawn | Check and service aerial platform | Shawn | 2022-11-18 | Closed | 2022-12-08 | Serviced autopilot, checked motor function
20 | 2022-11-10 | Shawn | Design Camera Enclosure in Fusion/Inventor | Shawn | 2022-11-18 | Closed | 2022-12-08
21 | 2022-11-10 | Shawn | Drawing and render for camera Enclosure | Shawn | 2022-11-18 | Closed | 2022-12-08
22 | 2022-11-10 | ALL | Work on PDR and finialize SDR | ALL | 2022-11-20 | Closed | 2022-12-08
23 | 2022-11-16 | Luke | Perform image filtering with color masking | Luke | 2022-11-20 | Closed | 2022-12-08
24 | 2022-11-20 | Luke | Compare Pi Cam and Webcam | Mikel | 2022-11-23 | Closed | 2022-12-08
25 | 2022-11-20 | Mikel | Update Bill of Materials | Mikel | 2022-11-20 | Closed |  | Added more materials and links to websites
26 | 2022-11-20 | Mikel | Start training AI model | Mikel | 2022-12-07 | Closed | 2022-12-18 | Trained AI model to distinguish between 3 types of flowers, goal was to get used to work with AI training models
27 | 2022-11-20 | Shawn | Create physical model in CAD | Shawn | 2022-12-05 | Closed | 2022-12-05
28 | 2022-11-28 | Luke | Trace objects with image overlays | Luke | 2022-12-08 | Open | 2022-12-08
29 | 2022-11-28 | Mikel | Preliminary AI Tests | Mikel | 2022-12-08 | Closed | 2022-12-18
30 | 2022-11-28 | Shawn | 3D Print physical model prototype | Shawn | 2022-12-08 | Open | 2022-12-08
31 | 2022-11-21 | ALL | Finish SRD and PDR | ALL | 2022-12-05 | Closed | 2022-12-04
32 | 2023-01-16 | Castellanos | Interview with Castellanos | ALL | 2023-01-16 | Closed | 2023-01-16 | Status Update
33 | 2023-01-16 | Mikel | Determine Meeting Time(s) for this semester | ALL | 2023-01-23 | Closed | 2023-01-25 | Group will meet at least once a week (prefered days: Mondays at 3pm or Fridays at 5pm)
34 | 2023-01-16 | Luke | Start working with object recognition | Luke | 2023-01-23 | Closed
35 | 2023-01-16 | Shawn | Start training AI model | Shawn | 2023-02-01 | Closed
36 | 2023-01-29 | Luke / Shawn | Meeting with Prof. Yilmaz | Luke / Shawn | 2023-01-30 | Closed |  | Keeping Dr. Yilmaz up to date and scheduling a meeting with the whole group (Mikel coulnt assist due to classes)
36 | 2023-01-30 | ALL | Start working on CDR | Mikel |  | Closed
37 | 2023-01-30 | ALL | Familiarize with OpenCV | Luke | 2023-02-14 | Closed
38 | 2023-01-30 | ALL | Communication planning | Shawn |  | Closed
39 | 2023-01-30 | Mikel | Create a preliminary website for the project | Mikel | 2023-02-07 | Closed |  | Preliminary website created
40 | 2023-02-07 | Shawn | Implement real-time object detection using Pytorch and OpenCV | Shawn |  | Closed
41 | 2023-02-07 | Luke | Run the program on the Jetson | Luke |  | Open |  | We have tested different programs on CPU but this is going to be the first time trying to run it using the Jetson
42 | 2023-02-07 | Mikel | Create separate branches and start adding information and images to the website | Mikel |  | Open
43 | 2023-02-14 | ALL | Team meeting to discuss and schedule next milestones | ALL | 2023-02-14 | Closed
44 | 2023-02-14 | ALL | Start working on Test Plan Document | ALL | 2023-02-22 | Closed
45 | 2023-02-22 | ALL | Finalize Test Plan Document | ALL | 2023-02-22 | Closed
46 | 2023-02-26 | Mikel/Luke | Finalize CDR document and PPT | Mikel/Luke | 2023-02-27 | Closed
47 | 2023-02-26 | ALL | Finalize Critical Assesment document | ALL | 2023-02-27 | Closed
48 | 2023-02-26 | Shawn | Print preliminary 3D model | Shawn | 2023-02-28 | Closed

## Accomplishments
Tri-Weekly status. The content of the weekly communication is:
a) Program schedule, technical and cost status
b) Significant accomplishments
c) Issues and resolution plans
d) Action items status
e) Provide date and time of meeting with the advisor
The purpose of this document is for the individual function Team/leads to provide current status in their specific area to be included in the project status
Need to provide progress against, at minimum: SRD, SRR, PDR, Website, schedule, WBS, BOM etc.
This Column tracks your significant accomplishments. You can use this to sub-tasks from your scheduled progress.
# | Week of Accomplishments | Description of Accomplishment | Notes
1 | 2022-09-08 | Meet with Dr. Yilmaz and team to coordinate new product development | Two types of anomolies: object type, speed type
1 |  |  | begin researching optical flow and object recognition
1 |  |  | Potential softwares: Yolo.v4, OpenCV (object recognition); PyTorch, Keras, TensorFlow
2 | 2022-09-15 | Self teach and team learning of machine learning. | Continuation of prior week
3 | 2022-09-22 | Self teach and team learning of machine learning. | Spoke to academic advisor via email and advisor gave super good input on the materials on what we are looking at and the materials
4 | 2022-09-29 | Activities cancelled due to Hurricane Ian
5 | 2022-10-06 | Self teach and team learning of machine learning. | Assembled the machine learning hardware.
6 | 2022-10-13 | Self teach and team learning of machine learning. | Ran machine learning on the hardware, training our first models.
7 | 2022-10-17 | loaded OS onto Raspberry Pi
8 | 2022-10-17 | Jetson Nano operational
9 | 2022-10-24 | SRD Document Verison 1.1 completed
10 | 2022-10-24 | Understanding of Multi-layered learning, Deep Learning, weights and biases, sigmod and ReLex operators. | These learning objects are a deep dive in how neuronetwork works. We are focusing on theory, rather than just running an algorithm on a computer and not knowing how it works.
11 | 2022-10-31 | Understanding of Gradient decent and training a nuero-networking using backpropagation. | These are critical objectives in designing, training, and fine-tuning our own or an exsist machine learning model.
12 | 2022-11-07 | Open CV running at linux enviroment | OpenCV running at a linux enviroment is the hallmark of everything we do in software. From this, traditional methods in video analytics in edge computing is done. We've de-facto performed "edge computing". Using more advanced algorithms, such as a ML network, follows.
13 | 2022-11-14 | Aerial/Physical Platform Operational | Examined possibility of utilizing aerial platform
14 | 2022-11-17 | Performed preliminary tests with the Jetson Nano and Image filtering | Color scaling
15 | 2022-12-21 | Created a CAD model for physical system | 3D CAD Model for the physical system that will house the hardware used in the project
16 | 2022-12-21 | PDR Presentation | PDR Presentation for class
17 | 2022-12-04 | Completed SRD Document | Complete, ensure the document is up-to-date, and review the SRD Document
18 | 2023-01-29 | Meeting with Dr. Yilmaz | Next meeting will be within the next 14 days, depending on the team's progress
19 | 2023-01-30 | Created a weekly work plan | Defined specific roles and milestones for each teammember for the next 4 weeks
20 | 2023-01-31 | Dropped raspberry pi to focus on working with the Jetson. | After meeting with Dr. Yilmaz, we decided to drop the raspberry pi. The idea is to focus on working with the Jetson to deliver our product on time.
21 | 2023-02-07 | GitHub website created | Changing the theme, adding images and tabs requires learning some coding and will be done within the next week
22 | 2023-02-07 | First AI trained model succesfully working | First model worked perfectly on CPU, next step would be testing it on the Jetson
23 | 2023-02-22 | Completed Test Document Plan
| 2023-02-25 | Bill of Materials Finalized | High value assets required to complete the first prototypeidentified.
| 2023-02-26 | Completed Final draft for prototype model | Final layout is finished from CAD program, 3D printing hardware fixtures and parts begun
24 | 2023-02-26 | Completed CDR Document and PowerPoint
25 | 2023-02-26 | Completed CA Document

## Project Schedule
This is notional template and dates need to alighn with class desginated dates and deadlines. As a team you need to further break down class deadlines to keep your team on track
| Desing I | [16 empty] | Design II - subject to change per design II Intructor
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Needs to Align with Instructors deadlines
Intructors Milestones
[11 empty] | SRD due |  |  |  |  | PDR |  |  |  | CDR | [11 empty] | Design Demonstration
Team Formation and Advisor established
WBS, Org. and Schedule due, embeded in excel
Requirements Doc Due ( Preliminary & Final )
Final Document Package due
Team/Student needs to provide further schedule detial to accomplish the tasks
Planning and Systems Engineering
Product Idea/Concept
System Engineering Managent Plan
System Requirements Document (SRD)
Design Document
Major Design Deadlines | Design II - subject to change per design II Intructor 22: Procure
Design, Procure, Build, & Test | Design II - subject to change per design II Intructor 25: Build; Design II - subject to change per design II Intructor 31: Test
Assembly of First Prototype
Sub Design and Development Tasks
Website
CDR
Test Plan Document
Essay
Poster
Video
Final Report
Assumptions:
Understanding of Machine Learning

## WBS
Team | Need to break down task so a single individual is responsible. For example, EE task can be broken for two individuals or more, as needed | By writing this, team member agrees to the task assignment | By writing this, team member agrees to the task assignment
Roles | Responsible Individual | TASK DESCRIPTION - Design I | TASK DESCRIPTION - Design II
MANAGEMENT |  |  |  | write the perceived detail
Technical Leader | Luke | Keep up to date with technical information and the application thereof to the project | Central communication with advisor and other members
Team Coordination Leader | Shawn | Coordinates Assets, Plans, and Time | Help organize the schedule and tasks ahead
Cost & Schedule leader | Mikel | Updates the schedules on this sheet and manages fiances during making purchasing decisions | Maintains budget and acquire funding
SYSTEM ENGINEERING
SYST ENGINEERING | Luke | This is a collaborative effort because our team is small and the task at hand is quite broad (applying machine learning). Each student will be tasked to learn as much as he can and help each other to be familar with the concepts of machine learning. | Overall archetecture of the system and suggests and finds system components | Example: SEMP Document
SYST ENGINEERING | Mikel | This is a collaborative effort because our team is small and the task at hand is quite broad (applying machine learning). Each student will be tasked to learn as much as he can and help each other to be familar with the concepts of machine learning. | Overall archetecture of the system and suggests and finds system components | Example: Requirements Documents
TEST ENGINEERING | Shawn | Shawn will be responsible in testing the system to see if it meets the expected requirements. | Perform tests, listed in the test requirement document, to quantify system performance
PROD ENGINEERING | Mikel |  | To embelish and package prototype as a product
CONFIG MGMT | Luke
RELIABILITY | Shawn | Shawn will be responsible in testing the system agasint expected enviroments. If the team decides to shift to building a robot, then Shawn will take the vehicle to subject it to noises expected. | Ensure repeatability of system and test system against adversary conditions
QUALITY | Mikel |  | Ensure prototype are built within specifications listed
PARTS MANAGEMENT | Luke |  | Ensure parts are avalible and manages part acquisitions
EMI / EMC | Shawn | Shawn will take account of EMI and EMC . If there are no equipments avalible to test these systems due to finanical restrictions, then theoritcal considerations and best practices will be implemented. | Ensure minimization of EM interference
SAFETY | Mikel |  | Ensure prototype meats saftey standards and check for potential hazards
Hardware
ELECT.DESIGN |  | All members will help distribute the task since it is such a small team. | All members will help distribute the task since it is such a small team.
DESIGN | Luke | Luke will focus on electrical hardware design. | Hardware hookups and soldering of electrical components
MECH. DESIGN
PSNA DESIGN | Shawn | Shawn will focus on mechanical design. | Design of layout and manufacture of mechanical components, including 3D printing
SOFTWARE
SW DEVELOPM | Mikel | Mikel will focus on the software design of the system. | Development of software
TEST Engineering
Test | Shawn | As mentioned above, shawn will perform and design tests for the system. | Design test and operation plans for the prototpe system
TEST SOFTWARE
DESIGN | Mikel | Mikel will perform and design tests for the software of the system. | Design test and operation plans for the software side of the system.

## BOM
Index | Component Name | Short description | function, how it is used in your system | Quantity | Cost | Reference or links to websites
1 | Jetson Nano Dev Kit | NVIDIA Jetson Nano Developer Kit-B01 | Jetson Nano. Used for hight speed video processing | 1 | 149 | https://www.seeedstudio.com/NVIDIA-Jetson-Nano-Development-Kit-B01-p-4437.html
2 | Sony IMX477R HQ Sensor | Two main sensor used for image processing | Image capture device used to acquire data | 2 | 100
3 | Theia TL1250 Lens | Telephoto lens for long focal distances | Focus for sensor 1 | 1 | 400 | https://www.pishop.us/product/raspberry-pi-camera-module-v2/?src=raspberrypi
4 | Theia TL410 Lens | Wide angle lens for wide field of view | Focus for sensor 2 | 1 | 400 | https://www.amazon.com/Acer-SB220Q-Ultra-Thin-Frame-Monitor/dp/B07CVL2D2S/ref=asc_df_B07CVL2D2S/?tag=&linkCode=df0&hvadid=309751315916&hvpos=&hvnetw=g&hvrand=2984751961022005895&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9012103&hvtargid=pla-623140191247&ref=&adgrpid=67183599252&th=1
5 | 20 Watt DC Power Supply | Power supply unit to power the entire system | Powering entire system | 1 | 12.99 | https://www.amazon.com/dp/B074FFM8NH/ref=asc_df_B074FFM8NH1668942000000?tag=cnet-buy-button-20&creative=395261&creativeASIN=B074FFM8NH&linkCode=asn&ascsubtag=4488de497d3f43d9b028b7b709b91106%7C0c51f952-23c5-46b9-9981-e666ddffc904%7Cdtp&th=1
6 | Jetson Nano Wireless Internet Adapter​ | Wifi adapter for debug and connectivity | Debug and communication | 1 | 18.99 | https://www.amazon.com/UGREEN-Transfer-Enclosures-Printers-Cameras/dp/B00P0E3954/ref=sr_1_2_sspa?gclid=Cj0KCQiAveebBhD_ARIsAFaAvrGmKD_6BYiGSyBMaOykmtG-7y-5g0AYURXQmgAFIiLV0Cve6tTJt_YaAvKmEALw_wcB&hvadid=616863166062&hvdev=c&hvlocphy=9012103&hvnetw=g&hvqmt=e&hvrand=7260197836364059012&hvtargid=kwd-2739326421&hydadcr=24662_13611802&keywords=usb%2Busb%2Bcable&qid=1668991145&sr=8-2-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&th=1
7 | PLA Filament 2KG | Materials needed for 3D printers | Needed to manufacture parts | 1 | 51 | https://www.amazon.com/AmazonBasics-Matte-Keyboard-QWERTY-Layout/dp/B07WJ5D3H4/ref=asc_df_B07WJ5D3H4/?tag=&linkCode=df0&hvadid=416694317409&hvpos=&hvnetw=g&hvrand=15199027512185915176&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9012103&hvtargid=pla-913716436783&ref=&adgrpid=94693386435&th=1
8 | Stepper Motors (Threaded Z Axis, Yaw Axis) Nema 17 | Driver for gimbal motion | Drive the yaw and r Z axis for camera pointing | 3 | 41.97 | https://www.amazon.com/Verbatim-Optical-Mouse-Accessibility-Compatible/dp/B00LPC3O3M/ref=sr_1_2_sspa?gclid=Cj0KCQiAveebBhD_ARIsAFaAvrHfeKxsZjww1gb-U-z-6kcb3bJSpWOKb5n6JWqrnU4v5QbZ4l-awHcaAuE6EALw_wcB&hvadid=616863247161&hvdev=c&hvlocphy=9012103&hvnetw=g&hvqmt=e&hvrand=16760430086096392764&hvtargid=kwd-2510389481&hydadcr=26614_11715055&keywords=usb+mouse&qid=1668992084&sr=8-2-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&psc=1
9 | High Torque Servo (Pitch Axis) Savox Sb2290Sg | Driver for Pitch Axis | Drive the pitch axis for camera porinting | 1 | 150
10 | Stepper Motor Driver Set TMC2208 | Stepper driver controller | It controls the stepper motors at a high power efficency | 1 | 10 | https://www.amazon.com/waveshare-Supply-100-240V-Adapter-Converter/dp/B0915J7BXL/ref=sr_1_7?crid=2PH8HGAJ73D1P&keywords=12v+power+supply+jetson+nano&qid=1668993724&sprefix=12v+power+supply+jetson+nano%2Caps%2C419&sr=8-7
11 | High Current 5V Step Down CC Bec Pro | High qualuity 5 volt power regulator | Needed for 5 volt servo | 1 | 50 | https://www.amazon.com/SanDisk-128GB-MicroSDXC-Memory-Adapter/dp/B0B7NTY2S6/ref=sr_1_5?gclid=Cj0KCQiAveebBhD_ARIsAFaAvrE08_fvhgToguZZ98vGk_q1sMuLYPPigwQ2reVOTupXX_kbTzz0IhcaAvLqEALw_wcB&hvadid=557586749177&hvdev=c&hvlocphy=9012103&hvnetw=g&hvqmt=e&hvrand=15603730328294678755&hvtargid=kwd-31052172773&hydadcr=18003_13447347&keywords=128gb%2Bmicrosd&qid=1668991406&sr=8-5&th=1
12 | Threaded Rods 3/8"-16 36" | Mechanical rots for Z axis retract | Needed to retract system for the camera | 2 | 12 | https://www.amazon.com/Geekworm-Adapter-Wireless-1200Mbps-Network/dp/B07TFT876R
13 | [5 empty] | https://www.amazon.com/Elegoo-EL-CP-004-Multicolored-Breadboard-arduino/dp/B01EV70C78/ref=asc_df_B01EV70C78/?tag=hyprod-20&linkCode=df0&hvadid=222785939698&hvpos=&hvnetw=g&hvrand=13549122753249701448&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9012103&hvtargid=pla-362913641420&psc=1
14
15
16
17
18